## Campaign Plan
Task ID | Task Name | Workstream | Owner | Start Date | End Date | Status
T-001 | Blog Post Series Draft | Content | Maya Patel | 2026-06-01 | 2026-06-17 | Complete
T-002 | Social Media Calendar | Content | Maya Patel | 2026-06-07 | 2026-06-21 | in progress
T-003 | Email Nurture Sequence | Content | Jordan Lee | 2026-06-14 | 2026-07-04 | In Progress
T-004 | Final Review | Content | Maya Patel | 2026-07-05 | 2026-07-12 | Not started
T-005 | Landing Page Mockup | Design | Alex Torres | 2026-06-01 | 2026-06-14 | Done
T-006 | Ad Creative Suite | Design | Alex Torres | 2026-06-08 | 2026-06-28 | Completed
T-007 | Email Template Design | Design | Priya Sharma | 2026-06-15 | 2026-07-01 | in progress
T-008 | Brand Asset Pack | Design | Priya Sharma | 2026-06-21 | 2026-07-07 | Not started
T-009 | Audience Segmentation | Paid Ads | Chris Nakamura | 2026-06-07 | 2026-06-18 | Complete
T-010 | Google Ads Campaign Setup | Paid Ads | Chris Nakamura | 2026-06-21 | 2026-07-08 | In Progress
T-011 | Meta Ads Campaign Setup | Paid Ads | Sam Okonkwo | 2026-06-22 | 2026-07-11 | in progress
T-012 | A/B Test Variants | Paid Ads | Sam Okonkwo | 2026-07-01 | 2026-07-18 | Not started
T-013 | Venue & Platform Booking | Launch Event | Jordan Lee | 2026-06-01 | 2026-06-10 | Done
T-014 | Speaker Coordination | Launch Event | Priya Sharma | 2026-06-14 | 2026-07-28 | Not started
T-015 | Final Review | Launch Event | Chris Nakamura | 2026-07-25 | 2026-08-04 | Not started